## Sheet1
Task | Assigned to | Progress | Last Updated | Notes
Home page | Maisee | Completed | 2026-09-17 | HTML done, needs CSS applied
Enroll student | Beatrice | Completed | 2026-09-19 | need to apply css
Add instructor | Beatrice | Completed | 2026-09-20
Add course | Maisee | Completed | 2026-09-17 | HTML done, needs CSS applied
Register course | Drew | Completed | 2026-09-20
Drop course | Drew | Completed | 2026-09-20
CSS | Maisee, Beatrice | Completed | 2026-09-17
Manuals | Beatrice | Completed | 2026-09-19 | need to apply css
README file | Drew | Completed
AI Usage Report | ALL | Completed
Group Peer Evaluations | ALL | Completed
MODULE TWO
Enroll Student validation (4 rules) | Beatrice | Not started
Add Instructor validation (4 rules) | Beatrice | Not started
Add Course validation (9 rules) | Maisee | Not started
Register Course validation (6 rules) | Drew | Not started
Drop Course validation (6 rules) | Drew | Not started
Enroll Student form display | Beatrice | Not started
Add Instructor form display | Beatrice | Not started
Add Course form display | Maisee | Not started
Register Course form display | Drew | Not started
Drop Course form display | Drew | Not started
Update select list display for Add Course | Maisee | Not started
Updating manuals | Beatrice & Maisee | Not started
README file | Maisee | Not started
AI Usage Report | ALL | Not started
Group Peer Evaluations | ALL | Not started
Any updates/fixes from Module 1 grade | ALL | In progress